****



**CONTRACTOR’S SITE PROGRESS REPORT**

**UPGRADING OF SONDA – DUNDUZU M1 ROAD AND CONSTRUCTION OF LUNYANGWA BRIDGE IN MZUZU CITY**

**PROCUREMENT REFERENCE No: MCC/WORKS/BRG/21/07/01 LOT 2**

**04th May, 2023**

1. **CONTRACT DETAILS** 
   1. Name of Contractor : SOS CONSTRUCTION
   2. Contract Sums : MWK 5,856,857,885.77
   3. Contract Duration : 1095 Days
   4. Commencement Date : 04th JULY, 2022
   5. Initial Completion Date : 02nd JULY, 2025
   6. Revised Completion Date :
   7. Time Elapsed : 304 Days
   8. Time Remaining **:** 791 Days
2. **WORKS IN PROGRESS**
   1. Surveying
   2. Stock piling of materials
3. **WORKS DONE**
   1. Cut to spoil from 0+000 – 2+700
   2. Roadbed preparation from 0+000 – 2+700
   3. Clearing and Grubbing from 0+000 – 5+840
   4. Fill on the Gully – completed
   5. Selected fill 0+000 – 2+700
   6. Subbase 0+000 – 2+000
   7. Construction of box culvert 0+020
   8. Construction of bush check dams
4. **PERSONELL**

In place

1. **MATERIALS/RESOURCES**

* gravel

1. **PLANTS & EQUIPMENTS**

**In place**

1. **QA/QC**
   * + test are being conducted and results submitted
2. **CRITICAL ISSUES AND CHALLENGES**
   * + Delay of payments
     + Escalation
3. **INFORMATION REQUIRED BY CONTRACTOR**
   * + Updated works order
     + Design
     + Update on IPC 2 & 4
4. **PROGRESS SUMMARY**
   1. **Physical** 
      * 19.03%
   2. **Time elapsed (to date 04/05/23)** 
      * 27.76%
   3. **Financial**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **IPC 1** | **IPC 2** | **IPC3** |
| **IPC amounts** | 964,091,833.05 | 149,153,538.33 | 149,442,387.62 |
| **Cumulative Percentage Progress** | - | 3% | 5% |
| **Status** | Paid | Not paid | Paid |
| **Date Submitted** | 27/07/2022 | 06/10/2022 | 13/12/2022 |
| **Date Paid** | 10/11/2022 | - | 28/04/2023 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **IPC 4** |  |  |
| **IPC amounts** | 104,580,926.77 | - | - |
| **Cumulative Percentage Progress** | 7% | - | - |
| **Status** | Not paid | - | - |
| **Date Submitted** | 07/02/2023 | - | - |
| **Date Paid** | - | - | - |

1. **ENVIRONMENTAL, HEALTH AND SAFETY ISSUES**

* We conducted sensitization meeting on 26th January 2023