****



**CONTRACTOR’S SITE PROGRESS REPORT**

**UPGRADING OF SONDA – DUNDUZU M1 ROAD AND CONSTRUCTION OF LUNYANGWA BRIDGE IN MZUZU CITY**

**PROCUREMENT REFERENCE No: MCC/WORKS/BRG/21/07/01 LOT 2**

**04th May, 2023**

1. **CONTRACT DETAILS**
	1. Name of Contractor : SOS CONSTRUCTION
	2. Contract Sums : MWK 5,856,857,885.77
	3. Contract Duration : 1095 Days
	4. Commencement Date : 04th JULY, 2022
	5. Initial Completion Date : 02nd JULY, 2025
	6. Revised Completion Date :
	7. Time Elapsed : 304 Days
	8. Time Remaining **:** 791 Days
2. **WORKS IN PROGRESS**
	1. Surveying
	2. Stock piling of materials
3. **WORKS DONE**
	1. Cut to spoil from 0+000 – 2+700
	2. Roadbed preparation from 0+000 – 2+700
	3. Clearing and Grubbing from 0+000 – 5+840
	4. Fill on the Gully – completed
	5. Selected fill 0+000 – 2+700
	6. Subbase 0+000 – 2+000
	7. Construction of box culvert 0+020
	8. Construction of bush check dams
4. **PERSONELL**

In place

1. **MATERIALS/RESOURCES**
* gravel
1. **PLANTS & EQUIPMENTS**

**In place**

1. **QA/QC**
	* + test are being conducted and results submitted
2. **CRITICAL ISSUES AND CHALLENGES**
	* + Delay of payments
		+ Escalation
3. **INFORMATION REQUIRED BY CONTRACTOR**
	* + Updated works order
		+ Design
		+ Update on IPC 2 & 4
4. **PROGRESS SUMMARY**
	1. **Physical**
		* 19.03%
	2. **Time elapsed (to date 04/05/23)**
		* 27.76%
	3. **Financial**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **IPC 1** | **IPC 2** | **IPC3** |
| **IPC amounts** | 964,091,833.05 | 149,153,538.33 | 149,442,387.62 |
| **Cumulative Percentage Progress** | - | 3% | 5% |
| **Status** | Paid | Not paid | Paid |
|  **Date Submitted** | 27/07/2022 | 06/10/2022 | 13/12/2022 |
| **Date Paid** | 10/11/2022 | - | 28/04/2023 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **IPC 4** |  |  |
| **IPC amounts** | 104,580,926.77 | - | - |
| **Cumulative Percentage Progress** | 7% | - | - |
| **Status** | Not paid | - | - |
| **Date Submitted** | 07/02/2023 | - | - |
| **Date Paid** | - | - | - |

1. **ENVIRONMENTAL, HEALTH AND SAFETY ISSUES**
* We conducted sensitization meeting on 26th January 2023